## Hoja1
Work Plan
Task | February |  |  |  | March
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Requirements
Client Requirements
Read Nora Sandler document
Install Elixir and Read Documentation
First Team Meeting
Stage 1: Lexer
Project Architecture Definition
Lexer Code
Stage 2: Parser
Second Team Meeting
Parser Code
Stage 3: Code Generator
x64 Instructions Set Review
Code Generator
Stage 4: Tests
Test Building
Final Team Meeting